# Yaadhum — Technical Team Build Plan

A short briefing: what we are building, in what order, with which tools, and how we beat the five problems that would otherwise sink it.

## 1. The stack — decided, with the reason in one line

| Concern | Choice | Why this one |
| --- | --- | --- |
| Database | PostgreSQL 16 (AWS RDS, ap-south-1) | One engine gives us relational integrity, pgvector for question embeddings, ltree for the syllabus tree, and row-level security for school isolation. No second datastore at pilot scale. |
| Cache / queue | Redis (ElastiCache) + arq | Background extraction jobs. Simpler than Celery, plenty at this volume. |
| Object storage | AWS S3, SSE-KMS, lifecycle rules (MinIO locally) | Page images, mark crops, assembled PDFs. Never in the database. |
| LLM | Claude — claude-opus-5 for high stakes, claude-haiku-4-5 for volume, Message Batches API overnight (50% cheaper) | Structured outputs and strict: true tools let us force schema-valid, FK-checkable output. Zero training needed to launch. |
| OCR | Not a single product — a layered stack: OpenCV (geometry, colour, blobs) + PaddleOCR (text detection, printed text) + the LLM for handwritten digits. pyzbar for QR. TrOCR fine-tune later. | Generic OCR products fail on "a red number somewhere in the margin". We localise deterministically and only ask a model to read one digit at a time. |
| Cloud | AWS `ap-south-1` (Mumbai) — ECS Fargate, or one EC2 + Docker Compose for the pilot | Children's data under the DPDP Act must stay in India. One school does not need Kubernetes. |
| Frontend | Next.js 15 + TypeScript + Tailwind + shadcn/ui | Test, scanner and dashboard are one deployable. |
| Offline / camera | Dexie (IndexedDB) + getUserMedia + OpenCV.js | School Wi-Fi will fail mid-scan. Capture must work with no network. |
| Backend | FastAPI (Python 3.12) + SQLAlchemy 2.0 + Alembic + Pydantic v2 | Same language as the CV and analysis layers — no service boundary in the middle of the algorithm. |
| Analysis | pandas · NumPy · SciPy · dbt → DuckDB (ClickHouse later) | Scoring, Wilson intervals, point-biserial, the solver. |
| Auth | Auth.js, roles + Postgres RLS | Students never get an account — a per-class code only. |
| Observability / CI | Sentry · OpenTelemetry · GitHub Actions | run_id propagated end to end so any number traces back to its source crop. |

The one architectural rule everybody must know: the system has seven layers and exactly one of them contains a model. Capture, restoration, colour separation, localisation, association, reconciliation and reporting are all deterministic OpenCV/SciPy/Python. Only recognition calls an LLM. That is why we can launch on a paid model and later swap in a free one by changing a config value.

## 2. Build order — seven phases

### P0 · Foundation — 2 days

Repo, Docker Compose (Postgres + Redis + MinIO), FastAPI + Next.js skeletons, CI.

Alembic migration: school, section, student_profile, taxonomy_node, chapter_weight,

assessment, question, question_skill, mark_event, data_quality_flag, analysis_run.

`ml_corpus` schema created now, not later — it must be writing from the first captured page.

Auth + school_id request context; every query filters on it.

Done when: docker compose up, alembic upgrade head, GET /health returns 200 with a live DB ping.

### P1 · Interest test (Use case 1) — 5 days

| Step | Method / algorithm | Library |
| --- | --- | --- |
| Consent + profile form | Schema-shared validation client and server | react-hook-form + Zod / Pydantic |
| 36 bilingual items, 6 screens | Scale-interleaved order, fixed seed per student | next-intl (EN/TA) |
| Autosave + resume | Write on every tap; resume by roll no + class code | Dexie |
| Validity screening | Long-string run, median item time, reverse-keyed pair inconsistency | NumPy |
| Scoring | Raw sums → ipsative centering (subtract person mean) → percentile with empirical-Bayes shrinkage | NumPy / SciPy |
| Interpretation | Holland top-3 code, differentiation D and consistency C; flat profile ⇒ no stream call | pure Python |
| Stream fit | 6×4 weight matrix as data, not code | Postgres table |
| Principal views | Student report, cohort dashboard, PDF | Jinja2 + WeasyPrint |

Done when: 40 seeded students score end to end, and a deliberately flat profile correctly withholds its recommendation.

### P2 · Capture + storage — 5 days

Camera component, quality gate before the shutter unlocks: blur (variance of Laplacian),

glare (bright-blob fraction), coverage (quad area), skew (top-edge angle) — all at ~10 fps.

Feature 1: single cover-page frame. Feature 2: multi-page scan with **per-page retake that keeps

the page's position**, reorder, delete, explicit Complete.

IndexedDB staging + thumbnails + 24-hour purge.

Resumable per-page upload; server assembles a lossless PDF (img2pdf embeds the original

JPEG bytes) with metadata (pikepdf); store the page images too, not only the PDF.

QR sticker → student binding, checked against the roster.

CSV/Excel import as a secondary path (wide and long shapes, dry-run diff, batch undo).

Done when: a teacher scans 15 pages for 5 students on a real phone, offline, without help.

### P3 · Question paper → frozen Q-matrix — 5 days

claude-opus-5 structured extraction: `section, question_no, sub_part, text, max_marks,

has_diagram, choice_group_id`.

Gate G1 Σ max_marks (respecting OR choice groups) == printed total.

G2 question sequence complete. G3 two independent passes agree, field by field.

Classification into chapter / sub-topic / R&U-AP-AEC: retrieve nearest validated library

questions → constrained prompt (only existing taxonomy IDs) → self-consistency k=5 → conformal abstention.

One teacher confirmation screen (~5 min, crop beside each row) → Q-matrix frozen and versioned.

Done when: a real past paper reconciles to its printed total and is confirmed in under 5 minutes.

### P4 · Mark extraction — 5 days (the core)

| Step | Method / algorithm | Library |
| --- | --- | --- |
| Restore | Corner detect → homography → illumination flattening by division → white balance → deskew | OpenCV |
| Separate ink | HSV banding; per-school hue centroids fitted by k-means (k=3) on ink pixels — unsupervised, 3 pages, no labels | OpenCV + scikit-learn |
| Anchors | Question labels from the student layer; closed-vocabulary filter against the frozen Q-matrix | PaddleOCR det + regex |
| Candidates | Isolated/circled numerals from the teacher layer; ticks, crosses, strikes excluded by shape; totals detected separately as extra equations | OpenCV contours |
| Recognise | MarkRecognizer.predict(crop, legal_values) → distribution over the legal values for that question | claude-haiku-4-5 (swap later) |
| Associate | Cost matrix (distance, answer-block containment, side consistency, value plausibility) → Hungarian algorithm; then refit the teacher's own convention and re-solve | scipy.optimize.linear_sum_assignment |
| Reconcile | max Σ log p s.t. grand + section + page totals, 0 ≤ m ≤ max, legal step lattice — exact DP | pure Python |
| Route | Calibrated confidence; auto-accept or review queue with the crop; flag, never guess | FastAPI + Next.js |

Done when: the solver corrects a planted misread, and an unreconcilable script flags instead of guessing.

### P5 · Analysis + report — 5 days

Marks → chapter / sub-topic / tier through the frozen Q-matrix. Loss with denominators, an evidence floor (under 2 marks ⇒ "insufficient evidence", never a percentage), Wilson intervals, board-weighted indicator with coverage gaps, paper quality (difficulty, point-biserial, Cronbach's α, χ² against 54/24/22). Principal report + PDF.

### P6 · Hardening + proof — 5 days

Audit sample and accuracy dashboard, threshold auto-tuning, RLS, consent and retention, load test, handover.

First real class through the system: end of P4, about three weeks.

## 3. The challenges, and how we beat each one

| # | Challenge | How we tackle it | Tool |
| --- | --- | --- | --- |
| 1 | Bad photos ruin everything downstream | Quality gate before the shutter unlocks — four metrics at 10 fps. A bad photo costs 5 s here, a wrong report later. | OpenCV.js |
| 2 | The mark is anywhere — left, right, above, inside the margin | Never use a fixed region. Anchor-first: find question labels, find mark blobs, then solve the binding as an assignment problem. | scipy Hungarian |
| 3 | Student's own working looks like a mark | Teacher writes red, student black/blue. Split the page into two masks; the mark detector never sees the student's arithmetic. | OpenCV HSV |
| 4 | Pen colour varies by school | Don't hardcode hues. Fit centroids with k-means on ink pixels from 3 unlabelled pages; re-fit automatically if confidence drops. | scikit-learn |
| 5 | Printed red margin rule lands in the teacher mask | Remove long straight structures first (long thin morphological opening + Hough) before any blob detection. | OpenCV |
| 6 | Handwritten 1 vs 3 — the most confusable pair | Don't fight it at the recogniser. The constraint solver uses the totals the teacher wrote: a wrong digit cannot satisfy the arithmetic. | pure Python DP |
| 7 | LLM hallucination | Four independent controls: the model never does arithmetic; output is schema-constrained and FK-validated so it cannot invent a chapter; the value enum is the legal marks for that question; two independent passes must agree. | Anthropic SDK structured outputs |
| 8 | Scripts attributed to the wrong student | Printed QR sticker on the cover, checked against the roster. Never handwritten-name matching. | pyzbar |
| 9 | School Wi-Fi drops mid-scan | Whole capture flow is offline-first; pages queue in IndexedDB; resumable per-page upload so a drop at page 14 does not lose 1–13. | Dexie + tus |
| 10 | We have no training data and no time to train | Launch on the paid model, log every prediction with its full distribution plus every human correction to ml_corpus. ~2,400 crops per class per term ⇒ enough to fine-tune the free recogniser within one term. | ml_corpus schema |
| 11 | CBSE internal choice ("attempt any one of Q31 or Q32") breaks the marks total | choice_group_id in the schema from day one — grouped questions contribute their marks once. Build it now or lose a sprint debugging a gate that was right. | Postgres |
| 12 | Tier (R&U / AP / AEC) is genuinely ambiguous | Conformal abstention with a coverage guarantee, then one teacher confirmation. Expect ~3× the abstention rate of chapter — that is correct behaviour, not a defect. | conformal calibration |
| 13 | Proving accuracy to a principal | Permanent audit sample: 10% of scripts re-keyed by hand including confident cells, error rate published on the dashboard. | dbt + dashboard |
| 14 | DPDP Act, children's data | Everything in ap-south-1; identity in a restricted schema; only crops of single digits cross the training boundary; consent_class set at capture time. | AWS + RLS |

## 4. Who does what

Frontend engineer — P1 test UI, P2 scanner and quality gate, P4 review queue, P5 dashboards.

Backend / CV engineer — P0 schema, P2 upload and PDF assembly, P4 layers L1–L6 (the hardest

and most valuable work in the project).

Full-stack / data — P3 question-paper pipeline and prompts, P5 analysis and reports, P6 audit

and accuracy dashboard. Owns ml_corpus end to end.

Parallelism: P1 and P2 can run side by side after P0. P3 and P4 can run side by side once the MarkRecognizer interface is agreed on day one of P4.

## 5. Three rules I want the team to hold

Never pay a model to find a rectangle. Localisation, geometry, colour and association are

deterministic code. This is a correctness decision, not a cost one — deterministic code cannot hallucinate.

Never overwrite a mark. mark_event is append-only; corrections are new rows. Audit trail,

OCR-versus-teacher reconciliation and correction history all come free from this one discipline.

Never guess. If the arithmetic does not reconcile, flag the script. A flagged script costs a

teacher thirty seconds; a silently wrong one costs the school relationship.

## 6. Blocking inputs

Five answer scripts photographed page by page on a teacher's own phone, in the room where

scanning will happen. Not flatbed scans. This calibrates the association weights and the ink profile.

Is a total written anywhere on the script — grand, per-section, per-page, or none? Each one is

an extra equation in the solver and directly improves accuracy.

Logo files (SVG + PNG) and brand colours.

Training-consent wording for the school agreement.